## Index
Commercial Book | Real Estate Web Application
Index
General Development Cycle
| Phase (Work Break Down) | Duration (% of Total Project Duration) | No. of ManDays / Cost
| Analysis and Design | 14 | 0
| Development (Coding) | 69 | 0
| Quality Control | 16 | 0
| Deployment | 1 | 0
| Total | 100 | 0
| COST (INR) |  | 0 | Plus Taxes

## Analysis & Design
Work Breakdown for Analysis and Design Phase
Module | Simple | Average | Complex
Requirement
Software Requirement Gathering and Analysis | 2
Software Requirement Specification (SRS) Document | 1
Design
Database design | 2
PSD Design (2 Iteration) for Web Interface | 5
Project Planning
Project Management Plan, communication and Schedule | 2
Total | 12 | 0 | 0
Effort Estimation
Work Complexity |  |  | Effort Required (Days)
Simple |  | 1 | 12
Medium |  | 2 | 0
Complex |  | 3 | 0
12
Total Coding Duration | 0 | Man days

## Development
Work Breakdown For Development/Implementation Phase
Module and Feature development | Simple | Average | Complex
Mobile App - Android & ios Hybrid
Login
Login via Facebook
| 0 | 0 | 0
Effort Estimation
Work Complexity |  |  | Effort Required (Days)
Simple |  | 1 | 0
Medium |  | 2 | 0
Complex |  | 3 | 0
|  | 4 | 0
Total Coding Duration | 0 | Man days

## Quality Control
Work Breakdown For Quality Control and Bug Fixing Phase
Module | Simple | Average | Complex
Quality Control & Bug Fixing
Functional Testing | 8
Compatibility Testing | 5
| 13 | 0 | 0
Effort Estimation
Work Complexity |  |  | Effort Required (Days)
Simple |  | 1 | 13
Medium |  | 2 | 0
Complex |  | 3 | 0
13
Total Coding Duration | 0 | Man days

## Deployment
Work Breakdown For Deployment Phase
Module | Simple | Average | Complex
Project Deployment
Deploy on server | 1
| 1 | 0 | 0
Effort Estimation
Work Complexity |  |  | Effort Required (Days)
Simple |  | 1 | 1
Medium |  | 2 | 0
Complex |  | 3 | 0
1
Total Coding Duration | 0 | Man days

## Assumptions
Sr. No. | Assumptions
Project Related Assumptions
1 | What are the different types of users required? Is there any admin user required?
2 | Are we accepting data from outside sources?
3
4
General Assumptions
1 | Resources will work in an off-shore model.
2 | Client will provide access to all required software, servers and paths if any.
3 | Any 3rd party software or services (e.g. Email gateway), etc. which is required to be integrated in the project will be purchased / provided by client.
4 | The Project plan may change as new information and issues are revealed.
5 | Additional charges will be imposed in case Client wish to make changes to the agreed upon project scope and objectives
6 | Any revisions in Graphic, Design, Functional and Non-Functional development efforts, after approval would fall under Change Request and charged extra as applicable.

## Compatibility
Browser
Windows OS | Google Chrome: 66

## Guidelines
Guidelines
General Development Cycle
Phase | Duration (% of Total Project Duration)
Analysis and Design | 14
Development (Coding) | 69
Quality Control | 16
Deployment | 1
Total | 100
Back to Index Page
Analysis and Design
Development (Coding)
Quality Control
Deployment